## Tasks
|  | Travel & tour Management System |  |  | Project End Date : |  | 2022-11-17
Sr. No | Module | Task Name | Task Status | Task Assign Date | Start Date | End Date | Remarks | Time Duration | Legends
[9 empty] | Status | Module
1 | Database. | create the database for the tms as design in the task sheet | Done | 2022-10-27 | 2022-10-28 | 2022-10-28 |  |  | Pending | Database.
2 | Database. | Insert appropriate data into tables | Pending | 2022-10-27 |  |  |  |  | In-progress | Backend.
3 | Database. | create the view or stored procedure for report. | Pending | 2022-10-27 |  |  |  |  | Done | front-end.
4 | Backend. | Create the spring boot project setup with log4j and connect MySQL database | Done | 2022-10-27 | 2022-10-28 | 2022-10-28 |  |  | error | Testing
5 | Backend. | CRUD for master actor | In-progress | 2022-10-27 | 2022-10-31
6 | Backend. | CRUD for master user | Pending | 2022-10-27
7 | Backend. | CRUD for master city | Pending | 2022-10-27
8 | Backend. | CRUD for master tour | Pending | 2022-10-27
9 | Backend. | CRUD for master vechile type. | Pending | 2022-10-27
10 | Backend. | CRUD for master vechile details. | Pending | 2022-10-27
11 | Backend. | CRUD for master status. | Pending | 2022-10-27
12 | Backend. | CRUD for vechile driver mapping. | Pending | 2022-10-27
13 | Backend. | API's for vechile travel journey. | Pending | 2022-10-27
14 | Backend. | API's for booking history | Pending | 2022-10-27
15 | front-end. | Create the angular app for tms and add bootstrap and angular material | Done | 2022-10-27 | 2022-10-30 | 2022-10-30
16 | front-end. | create separate routing components and services with respective | Pending | 2022-10-27
17 | front-end. |  | Pending | 2022-10-27
Note.
Make list of report can generate using this data
1. user travel journey.
2. Vechile travel journey.
3

## Database Design
Master User |  | master city |  | master tour |  | Master hotel |  | Master vechile type |  | Master Vechile Details
userId | pk | cityId | pk | tour Id | pk | Hotel Id | pk | vechileTypeId | pk | Vechile Id | pk
ActorId | fk | cityName |  | tour name |  | Hotel name |  | vechile Type Name |  | vechiletypeId | fk
first Name |  | state Id |  | tour description |  | Hotel type | ac/non ac | vechile type added Date |  | Vechile Name
Last Name |  | state |  | city Id |  | city Id |  | vechile type isDeleted |  | Company Name
password |  | pinCode |  | state Id |  | state Id |  |  |  | vechile Capcity
email |  | cityIsDeleted |  | tour price |  | No of rooms avaliable |  |  |  | vechile isDeleted
mobileNo | [5 empty] | hotel price |  | booking History
address | [7 empty] | booking Id | pk
gender |  | master Status |  | vechile travel journey |  |  |  | userId | fk
usercreated date |  | status Id | pk | vechilejourneyId | pk |  |  | mappingVechileDriverId | fk
userIsdeleted |  | status Name |  | vechileId | fk | mapping driver vechile details | pk | tour Id | fk
|  | status created Date |  | booking Id | fk | mappingVechileDriverId | fk | hotel Id | fk
|  | status is deleted |  | tour Id | fk | vechileId | fk | status Id
|  |  |  | status Id | fk | driverId |  | booking date
Master Actor | pk |  |  |  |  | from state |  | travelling startdate
actorId | [5 empty] | from city |  | travelling endDate
ActorName | [5 empty] | to state |  | total Amount
created Date | [5 empty] | to city |  | journeyIsDeleted
isDeleted | [5 empty] | vechile driver asign date
vechile driver journey start date
vechile driver journey end date
vechile fare
| 1 in master actor add |  | 2.Add ac/no ac in vechile type
Note | A.Admin B.User/traveller C.Driver
3 create the view or stored procedure as per requirement in the report section.