## Tasks
|  | Travel & tour Management System |  |  |  |  | Project End Date : |  | 2022-11-17
Sr. No | Module | Task Name | Task Status | Priority | Owner | Task Assign Date | Start Date | End Date | Remarks | Time Duration | Legends
[11 empty] | Status | Module | Owner
1 | Database. | create the database for the tms as design in the task sheet | Done |  | HW | 2022-10-27 | 2022-10-28 | 2022-10-28 |  |  | Pending | Database. | HW
2 | Database. | Insert appropriate data into tables | Pending |  |  | 2022-10-27 |  |  |  |  | In-progress | Backend. | SS
3 | Database. | create the view or stored procedure for report. | Pending |  |  | 2022-10-27 |  |  |  |  | Done | front-end.
4 | Backend. | Create the spring boot project setup with log4j and connect MySQL database | Done |  | HW | 2022-10-27 | 2022-10-28 | 2022-10-28 |  |  | error | Testing
5 | Backend. | CRUD for master actor | In-progress | 1 | HW | 2022-10-27 | 2022-10-31
6 | Backend. | CRUD for master user | Pending |  |  | 2022-10-27
7 | Backend. | CRUD for master city | In-progress | 1 | SS | 2022-10-27 | 2022-10-31
8 | Backend. | CRUD for master tour | Pending |  |  | 2022-10-27
9 | Backend. | CRUD for master vechile type. | Pending |  |  | 2022-10-27
10 | Backend. | CRUD for master vechile details. | Pending |  |  | 2022-10-27
11 | Backend. | CRUD for master status. | Pending |  |  | 2022-10-27
12 | Backend. | CRUD for vechile driver mapping. | Pending |  |  | 2022-10-27
13 | Backend. | API's for vechile travel journey. | Pending |  |  | 2022-10-27
14 | Backend. | API's for booking history | Pending |  |  | 2022-10-27
15 | front-end. | Create the angular app for tms and add bootstrap and angular material | Done |  | HW | 2022-10-27 | 2022-10-30 | 2022-10-30
16 | front-end. | create separate routing components and services with respective | Pending |  |  | 2022-10-27
17 | front-end. |  | Pending |  |  | 2022-10-27
18 | Database. | database backup and script of tables from mysql to .back file | Pending | 2 | HW\SS | 2022-10-31 | 2022-10-31 |  | check how to get backup and script of tables of mysql database
Note.
Make list of report can generate using this data
1. user travel journey.
2. Vechile travel journey.
3

## Database Design
Master User |  | master city |  | master tour |  | Master hotel |  | Master vehicle type |  | Master vehicle Details |  | mapping city routes
userId | pk | cityId | pk | tour Id | pk | Hotel Id | pk | vehicleTypeId | pk | vehicle Id | pk | routeId
ActorId | fk | cityName |  | tour name |  | Hotel name |  | vehicle Type Name |  | vehicletypeId | fk | routename
first Name |  | state Id |  | tour description |  | Hotel type | ac/non ac | vehicle type added Date |  | vehicle Name |  | source cityId
Last Name |  | state |  | city Id |  | city Id |  | vehicle type isDeleted |  | Company Name |  | source stateId
password |  | pinCode |  | state Id |  | state Id |  |  |  | vehicle Capcity |  | destination cityId
email |  | cityIsDeleted |  | tour price |  | No of rooms avaliable |  |  |  | vehicle isDeleted |  | destination stateId
mobileNo | [5 empty] | hotel price | [5 empty] | route created date
address | [11 empty] | routeIsDeleted
gender |  | mapping driver vehicle details | pk | vehicle booking details |  | booking History |  | master Status |  | vehicle travel journey
usercreated date |  | mappingvehicleDriverId | fk | vehicleBookingId |  | bookingHistory Id | pk | status Id | pk | vehiclejourneyId | pk
userIsdeleted |  | vehicleId | fk | userId |  | userId | fk | status Name |  | vehicleId | fk
|  | driverId |  | vehicleId |  | vehicleBookingId | fk | status created Date |  | bookingHistory Id | fk
|  | vehicle driver asign date |  | from stateId |  | tour Id | fk | status is deleted |  | tour Id | fk
|  | vehicle fare |  | from cityId |  | hotel Id | fk |  |  | status Id | fk
Master Actor | pk |  |  | to stateId |  | status Id
actorId |  |  |  | to cityId |  | booking date
ActorName |  |  |  | vehicle booking date |  | travelling startdate
created Date |  |  |  | vehicle journey start date |  | travelling endDate
isDeleted |  |  |  | vehicle journey end date |  | total Amount
|  |  |  | vehicle booking fare |  | journeyIsDeleted
| 1 in master actor add |  | 2.Add ac/no ac in vehicle type
Note | A.Admin B.User/traveller C.Driver
3 create the view or stored procedure as per requirement in the report section.